## jira
Epic | Issue key | Summary | Status | Issue Type | Parent id | Resolution
X-ES Xpedite 7674 Board Support | KSW-1 | Generalize the SBC boot sequence | Done | Story |  | Done
Standup integration lab environment for K3 | KSW-2 | Run K2 regression tests on Felix | Done | Story |  | Done
New software packaging for K3 | KSW-3 | Selectively include/build K3 SW projects on a .so basis | Done | Story |  | Done
X-ES Xpedite 7674 Board Support | KSW-4 | Verify that the 7672 boots after making the code changes. | In Progress | Story
X-ES Xpedite 7674 Board Support | KSW-5 | Verify that the 7672 still boots and the 7674 also boots after making any addition code changes. | In Progress | Story
Standup integration lab environment for K3 | KSW-6 | As a developer, I want to reconfigure all Felix SBCs to get to the current Red Hawk and latest Funnel Cake patch release so that I have solid baseline for future development/regression testing. | Done | Story |  | Done
Standup integration lab environment for K3 | KSW-7 | Configure Felix for use with regression testing | Done | Story |  | Done
Standup integration lab environment for K3 | KSW-8 | Double-check that the router daughter card is not on the Felix switch (and if it is, have it removed). | Done | Task |  | Done
X-ES Xpedite 7674 Board Support | KSW-9 | Update k3_sf2_software project to support SHT35 | In Progress | Story
ABEU Boot | KSW-10 | [ABEU_BOOT] Umbrella: Networked Node Boot change (all ABEUs and SCU slot 1 processor) | In Progress | Story
ABEU Boot | KSW-11 | [ABEU_BOOT] Tactical mode - networked node | In Progress | Story
ABEU Boot | KSW-12 | [ABEU_BOOT] Tactical mode - SCU slot 0 processor | In Progress | Story
ABEU Boot | KSW-13 | [ABEU_BOOT] UDP library Configured as server | Done | Story |  | Done
ABEU Boot | KSW-14 | [ABEU_BOOT] UDP library Configured as client | In Review | Story
Disable ssh access to radar | KSW-15 | Disable pushing down of scripts to the SCU | In Progress | Story
Disable ssh access to radar | KSW-16 | Disable Secure Shell (SSH) | In Progress | Story
Standup integration lab environment for K3 | KSW-17 | Configure the lab machines in MC039 to enable work to be performed in that environment. | In Progress | Story
Standup integration lab environment for K3 | KSW-18 | Prepare the lab for the inclusion of the String Test Set. | In Progress | Story
Standup integration lab environment for K3 | KSW-19 | Setup the air-cooled chassis, Wilma, in MC039. | In Progress | Story
Standup integration lab environment for K3 | KSW-20 | Setup in a K2 configuration as a baseline. | In Progress | Sub-task | 51425
Standup integration lab environment for K3 | KSW-21 | Setup in a 7674 configuration. | In Progress | Sub-task | 51425
Standup integration lab environment for K3 | KSW-22 | Setup in a 7674 with XMC. | In Progress | Sub-task | 51425
Disable ssh access to radar | KSW-23 | Move the Util scripts onto the SCU SBC | Blocked | Story
Disable ssh access to radar | KSW-24 | Disable the uploading of the old scripts | Done | Story |  | Done
Change SSD encryption scheme | KSW-25 | [SSD_AUTH] SSD Zeroisation and re-imaging | In Progress | Story
Filtered logging | KSW-26 | Pathfinding: Determine log file Jira stories | Done | Story |  | Done
New software packaging for K3 | KSW-27 | Create Jenkins job to execute Unit Tests | Done | Story |  | Done
Change SSD encryption scheme | KSW-28 | Path finding for hard drive Zeroization | Done | Story |  | Done
Filtered logging | KSW-29 | Create ability to disable all logging | New | Story
Filtered logging | KSW-30 | Create ability to disable logging of individual messages | New | Story
Filtered logging | KSW-31 | Learn what logs are created and collect example logs from actual runs. | Done | Story |  | Done
New software packaging for K3 | KSW-32 | Placeholder story for generating K3 Git transition tutorial/documentation. | New | Story
X-ES Xpedite 7674 Board Support | KSW-33 | Placeholder for UEFI story | New | Story
X-ES Xpedite 7674 Board Support | KSW-34 | Create a 7674 Coreboot Synergy project | Done | Story |  | Done
VLAN networking | KSW-35 | Document how to VLAN the SCU switch | Done | Story |  | Done
Disable ssh access to radar | KSW-36 | Understand how keys will work in K3 between radar and tactical/maint laptop | In Progress | Story
Change SSD encryption scheme | KSW-37 | Create a class so the radar can zeroize its drive at boot and run time | New | Story
New software packaging for K3 | KSW-38 | Use gcov and find a way to get regression test coverage | New | Story
New software packaging for K3 | KSW-39 | Migrate Synergy projects to Git repo | Done | Story |  | Done
New software packaging for K3 | KSW-40 | Copy K3-database-specific Synergy projects to the product line Synergy database. | Done | Story |  | Done
New software packaging for K3 | KSW-41 | Move completed tasks from K3 Synergy database to K2 sandbox/Git. | Done | Story |  | Done
Filtered logging | KSW-42 | Analyze the logs produced by the BallisticTrajectory project | Done | Story |  | Done
Filtered logging | KSW-43 | Analyze the logs produced by the C2_Comm project | Done | Story |  | Done
Filtered logging | KSW-44 | [LOGGING] Analyze the logs produced by the CoreSW_Linux project | Done | Story |  | Done
Filtered logging | KSW-45 | Analyze the logs produced by the INS_Proxy project | Done | Story |  | Done
Filtered logging | KSW-46 | [LOGGING] Analyze the logs produced by the MFRFS project | Done | Story |  | Done
Filtered logging | KSW-47 | [LOGGING] Analyze the logs produced by the MFRFS_Common project | Done | Story |  | Done
Filtered logging | KSW-48 | [LOGGING] Analyze the logs produced by the MFRFS_Health project | Done | Story |  | Done
Filtered logging | KSW-49 | [LOGGING] Analyze the logs produced by the NetworkSwitch_XCHANGE3013 project | Done | Story |  | Done
Filtered logging | KSW-50 | [LOGGING] Analyze the logs produced by the NeuralNetwork project | Done | Story |  | Done
X-ES Xpedite 7674 Board Support | KSW-51 | Verify on SBC 7672 board that RedHawk OS can be booted out of USB | Done | Story |  | Done
VLAN networking | KSW-52 | How do I configure the switch from the serial port to set the VLAN in maintenance in the factory. | Blocked | Story
ABEU Boot | KSW-53 | Pathfinding: Can you reprogram a SCIM from an ABEU? | Done | Story |  | Done
Filtered logging | KSW-54 | Determine what the logging approach with Systems/Modes | Blocked | Story
ABEU Boot | KSW-55 | [ABEU_BOOT] SCU needs to strip SCU-related boot map entries before sending the boot map to the ABEUs. | Done | Story |  | Done
X-ES Xpedite 7674 Board Support | KSW-56 | Study/document Core exeCswBoot to understand the current boot processing to share with the rest of the team. | Done | Story |  | Done
Standup integration lab environment for K3 | KSW-57 | Help Abram Nothnagle get up to speed on using RTSGE on an air-cooled chassis. | In Progress | Story
Filtered logging | KSW-58 | [LOGGING] Create a tool to comb through regression test logs to validate that logging restrictions are effective. | New | Story
Filtered logging | KSW-59 | [LOGGING] Document whether logs used for troubleshooting fall into tactical, engineering, and/or wireless categories. | New | Story
VLAN networking | KSW-60 | Characterize switch behavior with Xeon-D held in reset. | New | Story
| KSW-61 | Placeholder: Update panels software as needed. | New | Story
| KSW-62 | Jose to work with Hannah on C2_Comm unit test commenting. | Done | Story |  | Done
Standup integration lab environment for K3 | KSW-63 | Help configure desktop for VPN connections for remote users. | Done | Story |  | Done
X-ES Xpedite 7674 Board Support | KSW-64 | Test new OS image with new 7674 Extreme Linux drivers on Xpedite7674 | New | Story
ABEU Boot | KSW-65 | Create a UDP interface that receives commands and replies with a status | In Progress | Story
| KSW-66 | [BUFFER] Placeholder story to absorb pop-up stories during the sprint. | New | Story
ABEU Boot | KSW-67 | [ABEU BOOT 2] UDP Client/Server | New | Story
ABEU Boot | KSW-68 | [ABEU BOOT 2] ABEU Request for its Load on AirCooled | In Progress | Story
ABEU Boot | KSW-69 | [ABEU BOOT 2] SBC0 to SCIM Config Data request | In Progress | Story
ABEU Boot | KSW-70 | [ABEU BOOT 2] TRUI to SCU SBC0 ssh setup | New | Story
ABEU Boot | KSW-71 | [ABEU BOOT 2] SSD Drive Management | New | Story
Change SSD encryption scheme | KSW-72 | SSD recovery after writing bad key then good key | In Progress | Story
ABEU Boot | KSW-73 | [ABEU BOOT 2] ABEU Request for its Load on String | New | Story
Standup integration lab environment for K3 | KSW-74 | Install and configure two additional landing machines to support WFH | In Progress | Story

## abeu
Epic | Issue key | Summary | Status
ABEU Boot | KSW-10 | [ABEU_BOOT] Umbrella: Networked Node Boot change (all ABEUs and SCU slot 1 processor) | In Progress
ABEU Boot | KSW-11 | [ABEU_BOOT] Tactical mode - networked node | In Progress
ABEU Boot | KSW-12 | [ABEU_BOOT] Tactical mode - SCU slot 0 processor | In Progress
ABEU Boot | KSW-13 | [ABEU_BOOT] UDP library Configured as server | Done
ABEU Boot | KSW-14 | [ABEU_BOOT] UDP library Configured as client | In Review
ABEU Boot | KSW-53 | Pathfinding: Can you reprogram a SCIM from an ABEU? | Done
ABEU Boot | KSW-55 | [ABEU_BOOT] SCU needs to strip SCU-related boot map entries before sending the boot map to the ABEUs. | Done
ABEU Boot | KSW-65 | Create a UDP interface that receives commands and replies with a status | In Progress
ABEU Boot | KSW-67 | [ABEU BOOT 2] UDP Client/Server | New
ABEU Boot | KSW-68 | [ABEU BOOT 2] ABEU Request for its Load on AirCooled | In Progress
ABEU Boot | KSW-69 | [ABEU BOOT 2] SBC0 to SCIM Config Data request | In Progress
ABEU Boot | KSW-70 | [ABEU BOOT 2] TRUI to SCU SBC0 ssh setup | New
ABEU Boot | KSW-71 | [ABEU BOOT 2] SSD Drive Management | New
ABEU Boot | KSW-73 | [ABEU BOOT 2] ABEU Request for its Load on String | New

## ssd
Epic | Issue key | Summary | Status
Change SSD encryption scheme | KSW-25 | [SSD_AUTH] SSD Zeroisation and re-imaging | In Progress
Change SSD encryption scheme | KSW-28 | Path finding for hard drive Zeroization | Done
Change SSD encryption scheme | KSW-37 | Create a class so the radar can zeroize its drive at boot and run time | New
Change SSD encryption scheme | KSW-72 | SSD recovery after writing bad key then good key | In Progress

## ssh
Epic | Issue key | Summary | Status
Disable ssh access to radar | KSW-15 | Disable pushing down of scripts to the SCU | In Progress
Disable ssh access to radar | KSW-16 | Disable Secure Shell (SSH) | In Progress
Disable ssh access to radar | KSW-23 | Move the Util scripts onto the SCU SBC | Blocked
Disable ssh access to radar | KSW-24 | Disable the uploading of the old scripts | Done
Disable ssh access to radar | KSW-36 | Understand how keys will work in K3 between radar and tactical/maint laptop | In Progress

## logging
Epic | Issue key | Summary | Status
Filtered logging | KSW-26 | Pathfinding: Determine log file Jira stories | Done
Filtered logging | KSW-29 | Create ability to disable all logging | New
Filtered logging | KSW-30 | Create ability to disable logging of individual messages | New
Filtered logging | KSW-31 | Learn what logs are created and collect example logs from actual runs. | Done
Filtered logging | KSW-42 | Analyze the logs produced by the BallisticTrajectory project | Done
Filtered logging | KSW-43 | Analyze the logs produced by the C2_Comm project | Done
Filtered logging | KSW-44 | [LOGGING] Analyze the logs produced by the CoreSW_Linux project | Done
Filtered logging | KSW-45 | Analyze the logs produced by the INS_Proxy project | Done
Filtered logging | KSW-46 | [LOGGING] Analyze the logs produced by the MFRFS project | Done
Filtered logging | KSW-47 | [LOGGING] Analyze the logs produced by the MFRFS_Common project | Done
Filtered logging | KSW-48 | [LOGGING] Analyze the logs produced by the MFRFS_Health project | Done
Filtered logging | KSW-49 | [LOGGING] Analyze the logs produced by the NetworkSwitch_XCHANGE3013 project | Done
Filtered logging | KSW-50 | [LOGGING] Analyze the logs produced by the NeuralNetwork project | Done
Filtered logging | KSW-54 | Determine what the logging approach with Systems/Modes | Blocked
Filtered logging | KSW-58 | [LOGGING] Create a tool to comb through regression test logs to validate that logging restrictions are effective. | New
Filtered logging | KSW-59 | [LOGGING] Document whether logs used for troubleshooting fall into tactical, engineering, and/or wireless categories. | New

## pkg
Epic | Issue key | Summary | Status
New software packaging for K3 | KSW-3 | Selectively include/build K3 SW projects on a .so basis | Done
New software packaging for K3 | KSW-27 | Create Jenkins job to execute Unit Tests | Done
New software packaging for K3 | KSW-32 | Placeholder story for generating K3 Git transition tutorial/documentation. | New
New software packaging for K3 | KSW-38 | Use gcov and find a way to get regression test coverage | New
New software packaging for K3 | KSW-39 | Migrate Synergy projects to Git repo | Done
New software packaging for K3 | KSW-40 | Copy K3-database-specific Synergy projects to the product line Synergy database. | Done
New software packaging for K3 | KSW-41 | Move completed tasks from K3 Synergy database to K2 sandbox/Git. | Done

## lab
Epic | Issue key | Summary | Status
Standup integration lab environment for K3 | KSW-2 | Run K2 regression tests on Felix | Done
Standup integration lab environment for K3 | KSW-6 | As a developer, I want to reconfigure all Felix SBCs to get to the current Red Hawk and latest Funnel Cake patch release so that I have solid baseline for future development/regression testing. | Done
Standup integration lab environment for K3 | KSW-7 | Configure Felix for use with regression testing | Done
Standup integration lab environment for K3 | KSW-8 | Double-check that the router daughter card is not on the Felix switch (and if it is, have it removed). | Done
Standup integration lab environment for K3 | KSW-17 | Configure the lab machines in MC039 to enable work to be performed in that environment. | In Progress
Standup integration lab environment for K3 | KSW-18 | Prepare the lab for the inclusion of the String Test Set. | In Progress
Standup integration lab environment for K3 | KSW-19 | Setup the air-cooled chassis, Wilma, in MC039. | In Progress
Standup integration lab environment for K3 | KSW-20 | Setup in a K2 configuration as a baseline. | In Progress
Standup integration lab environment for K3 | KSW-21 | Setup in a 7674 configuration. | In Progress
Standup integration lab environment for K3 | KSW-22 | Setup in a 7674 with XMC. | In Progress
Standup integration lab environment for K3 | KSW-57 | Help Abram Nothnagle get up to speed on using RTSGE on an air-cooled chassis. | In Progress
Standup integration lab environment for K3 | KSW-63 | Help configure desktop for VPN connections for remote users. | Done
Standup integration lab environment for K3 | KSW-74 | Install and configure two additional landing machines to support WFH | In Progress

## vlan
Epic | Issue key | Summary | Status
VLAN networking | KSW-35 | Document how to VLAN the SCU switch | Done
VLAN networking | KSW-52 | How do I configure the switch from the serial port to set the VLAN in maintenance in the factory. | Blocked
VLAN networking | KSW-60 | Characterize switch behavior with Xeon-D held in reset. | New

## xes
Epic | Issue key | Summary | Status
X-ES Xpedite 7674 Board Support | KSW-1 | Generalize the SBC boot sequence | Done
X-ES Xpedite 7674 Board Support | KSW-4 | Verify that the 7672 boots after making the code changes. | In Progress
X-ES Xpedite 7674 Board Support | KSW-5 | Verify that the 7672 still boots and the 7674 also boots after making any addition code changes. | In Progress
X-ES Xpedite 7674 Board Support | KSW-9 | Update k3_sf2_software project to support SHT35 | In Progress
X-ES Xpedite 7674 Board Support | KSW-33 | Placeholder for UEFI story | New
X-ES Xpedite 7674 Board Support | KSW-34 | Create a 7674 Coreboot Synergy project | Done
X-ES Xpedite 7674 Board Support | KSW-51 | Verify on SBC 7672 board that RedHawk OS can be booted out of USB | Done
X-ES Xpedite 7674 Board Support | KSW-56 | Study/document Core exeCswBoot to understand the current boot processing to share with the rest of the team. | Done
X-ES Xpedite 7674 Board Support | KSW-64 | Test new OS image with new 7674 Extreme Linux drivers on Xpedite7674 | New